## Sheet1
Factors | Simple | Medium | Complex
Inputs | 3 | 4 | 8
Outputs | 2 | 3 | 7
Entities | 7 | 10 | 13
Interfaces | 5 | 7 | 10
Inquiries | 4 | 6 | 8
Count | Simple | Medium | Complex
Inputs | 0 | 4 | 1
Outputs | 2 | 2 | 1
Entities | 21 | 11 | 4
Interfaces (all maintenances) | 17 | 5 | 4
Inquiries (all reports) | 27 | 2 | 0
Total= | 67 | 24 | 10
Function Point Analysis Matrix | Simple | Medium | Complex | Total
Inputs | 0 | 16 | 8 | 24
Outputs | 4 | 6 | 7 | 17
Entities | 147 | 110 | 52 | 309
Interfaces | 85 | 35 | 40 | 160
Inquiries | 108 | 12 | 0 | 120
|  |  | RAW F.P. | 630
Additional Factors
Staff Experience with 4 GL tool | 3
Application uses Distributed Data Architecture | 4
Experience with Mobile Applications | 2
Utilization of Credit Card Gateway | 5
Developers are in different physical locations | 1
Utilizes SQLite and MS SQL | 2
Sum of Scores | 17
Adjusted F.P. | 516.6
Productivity (6 hours of the day) | 0.25
Number of Days (Productivity * Adjusted F.P.) | 129.15

## Sheet2
Iterative Development Estimate
Category | PC (Program Count) | PI (PrototypeDays) | ID (Iterative) | SC (completion)
Easy | 44 | 22 | 11 | 3.3
Simple | 19 | 28.5 | 28.5 | 14.25
Moderate | 27 | 81 | 121.5 | 101.25
Complex | 9 | 54 | 108 | 121.5
Total | 99 | 185.5 | 269 | 240.3
Calculation | Count | PC * Ratio | PI*Ratio | (PI+ID) *SC Ratio
Program Counts | Simple | Easy | Medium | Complex
| 44 | 19 | 27 | 9
Effort Estimations To Complete System
Category | 1st Prototype Days | Development Ratio | System Ratio
Easy | 0.5 | 0.5 | 0.1
Simple | 1.5 | 1 | 0.25
Moderate | 3 | 1.5 | 0.5
Complex | 6 | 2 | 0.75
Calculation | P1 | ID = P1*Ratio | SC = (P1+ID)*Ratio